## TODO
To Do
Joel: Frontend
✓ | Task | Goal
TRUE | Scaffold the Next.js app | create the Next.js project in apps/kiosk with a clean structure for components, hooks, and lib code. This is the base for all the other tasks.
TRUE | /: live camera view and take-photo button | show the live camera feed and a “Take photo” button, and keep the page full-screen and touch-friendly since it runs on a kiosk.
TRUE | 10-second countdown, then capture | when the button is pressed, show a visible countdown, then grab a frame from the video and turn it into a JPEG.
TRUE | Generate the photo ID and open the WebSocket with it | generate a unique photo ID and open the WebSocket with it (e.g. ?photoId=...) before uploading. The result can only reach the kiosk if the connection already exists.
TRUE | Request a presigned URL and upload to raw/{photoId}.jpg | ask Tom's endpoint for an upload URL, then PUT the JPEG straight to S3 at raw/{photoId}.jpg. The upload must not go through your server.
TRUE | Show “processing” and error states | show clear screens for connecting, uploading, processing, done, and error, plus a “Try again” path.
TRUE | Display the final photo on done | on {status: "done", key}, display the image from https://{CLOUDFRONT_DOMAIN}/{key}, read from NEXT_PUBLIC_CLOUDFRONT_DOMAIN. Then reset the kiosk for the next guest.
FALSE | /print: admin gate, list of processed photos, print button | if the WebSocket drops mid-session, reconnect automatically so the guest isn’t stuck. Also, gate the page so only admins can open it, list processed photos from final/ through a server route, display them using CloudFront URLs, and add a print button.
FALSE | Reconnect handling if the WebSocket drops | gate the page so only admins can open it, list the processed photos from final/, and add a print button. The list needs a way to read S3. A Next.js server route that lists final/ and returns presigned GET URLs is the simplest option.
Lleyton: Lambda functions
✓ | Task | Goal
TRUE | Lambda handler triggered by the S3 ObjectCreated event on raw/ | receive the S3 ObjectCreated event, extract the bucket and key, and derive the photo ID from the key.
TRUE | Read the raw photo from S3 | download raw/{photoId}.jpg into memory.
TRUE | Bedrock call for background removal. Check the model and region works first. | send the photo to the Bedrock image model and get back a cutout with transparency. Test this first, since it’s the riskiest part: confirm the model is available in your region and that your account has access enabled.
TRUE | Load the background and frame from assets/ | fetch the selected background and frame from assets/. Cache them between invocations to save time.
TRUE | Sharp compositing in the order background, cutout, frame | layer them in this order: background, then the cutout, then the frame. Resize the cutout to fit the background.
TRUE | Write final/{photoId}.jpg | save to final/{photoId}.jpg with ContentType: image/jpeg and a CacheControl header, which CloudFront and browsers will use. The key comes from the photo ID, so a retried event overwrites instead of duplicating.
TRUE | Look up the connection ID and send the result with PostToConnection. Ignore GoneException. | look up the connection ID in DynamoDB and send the done message with PostToConnection. If you get a GoneException, the kiosk left, so ignore it.
TRUE | Send error messages on failure and update the status in DynamoDB | if anything fails, update the DynamoDB status to error and send an error message so the kiosk doesn’t wait forever.
TRUE | Test locally with sample photos | run the pipeline against sample photos without deploying.
TRUE | Tune memory and timeout | set memory to 1.5–3 GB and the timeout to 60s or more.
TRUE | Package Sharp for the Lambda runtime. | Sharp needs Linux binaries to run on Lambda, so install with the Lambda platform in mind.
Tom: Backend
✓ | Task | Goal
TRUE | $connect Lambda: save the photo ID and connection ID with status and a one-hour TTL | read the photo ID from the query string and save {photoId, connectionId, status: "connected", ttl} in DynamoDB. The TTL is one hour from now.
TRUE | $disconnect Lambda: remove the mapping | remove the mapping for that connection.
TRUE | Presigned URL Lambda for raw/{photoId}.jpg, short-lived | return a short-lived upload URL for raw/{photoId}.jpg. Validate the photo ID, and keep the URL expiry to a few minutes.
TRUE | Final-image delivery (presigned GET URLs, or CloudFront if time allows) | define how the kiosk turns a done message into a displayable image. The kiosk builds the URL as https://{CLOUDFRONT_DOMAIN}/{key} (for example, https://dxxxx.cloudfront.net/final/{photoId}.jpg).
TRUE | Verify the photo ID is passed on connect (query string works well) | keep the DynamoDB status field accurate (connected, processing, done, error), coordinating with Lleyton on who writes each transition.
TRUE | End-to-end test script that uploads a photo and waits for the WebSocket result | connect a WebSocket, upload a test photo, wait for done, then fetch the CloudFront URL and confirm it returns HTTP 200 with image/jpeg.
TRUE | Prepare the sample frames and backgrounds for the first event | prepare the sample frames and backgrounds and put them in assets/ using the agreed folder layout
Ryan: Infrastructure
✓ | Task | Goal
FALSE | Storage stack (storage.yaml): S3 bucket, CORS, and DynamoDB table with TTL | the S3 bucket (with raw/, final/, assets/), CORS so browsers can upload directly, and the DynamoDB table with TTL enabled on ttl.
FALSE | Realtime stack (realtime.yaml): API Gateway WebSocket API with connect and disconnect routes | the WebSocket API with $connect and $disconnect routes, a stage, and the Lambda integrations and permissions.
FALSE | Processing stack (processing.yaml): processing Lambda and the S3 raw/ upload trigger | the processing Lambda with its memory and timeout, plus the S3 event notification. Filter the trigger to the raw/ prefix only, or writing to final/ would cause an infinite loop.
FALSE | Define least-privilege IAM roles for every Lambda | least-privilege roles for S3, DynamoDB, bedrock:InvokeModel, and execute-api:ManageConnections (needed for PostToConnection).
FALSE | Delivery stack (delivery.yaml): CloudFront distribution with a private S3 origin using Origin Access Control | a CloudFront distribution with the S3 bucket as its origin, using Origin Access Control so the bucket stays private. The bucket policy lets CloudFront read final/* only, so raw/ and assets/ are never exposed. Redirect HTTP to HTTPS and set a sensible default TTL.
FALSE | Parent stack (main.yaml) to connect the four stacks and pass values between them | wire the four stacks together. The delivery stack depends on the storage stack.
FALSE | Export stack outputs and parameters for the team: bucket name, table name, WebSocket URL, and CloudFront domain | export the bucket name, table name, WebSocket URL, and CloudFront domain so the others can plug them in.
FALSE | Write the deployment script and environment files (deploy.sh, dev.json, prod.json) | deploy.sh plus dev and prod parameter files for repeatable deploys.